## Estimated
SPRINT 1 PLANNING
Team Availibility
| Name | Available Hours | Estimation Total
| Le Nguyen Hoang Van | 76 | 304 | [12 empty] | On Time
| Luong Minh Hieu | 76 | [13 empty] | Lately
| Tran Quang Khai | 76 | [13 empty] | Early
| Nguyen Dinh Luu | 76 | [13 empty] | Unfinished
Sprint | Component | Task name | Reponsible Member | Total | Actual | 2020-02-17 | 2020-02-18 | 2020-02-19 | 2020-02-20 | 2020-02-21 | 2020-02-24 | 2020-02-25 | 2020-02-26 | 2020-02-27 | 2020-02-28
1 | Initial Sprint 1 | Adjust backlog | All member | 96 | 96 | 2020-02-17: 64; 2020-02-18: 32; 2020-02-19: 0
|  | Config GCP | Van | 8 | 8 | 2020-02-17: 8; 2020-02-18: 8; 2020-02-19: 8; 2020-02-20: 0
|  | Create Gitlab repository | Van | 4 | 4 | 2020-02-17: 4; 2020-02-18: 4; 2020-02-19: 4; 2020-02-20: 0
|  | Config Firebase | Van, Luu | 8 | 8 | 2020-02-17: 4; 2020-02-18: 4; 2020-02-19: 4; 2020-02-20: 0
| Design | Create prototype | Van | 8 | 8 | 2020-02-17: 8; 2020-02-18: 8; 2020-02-19: 8; 2020-02-20: 8; 2020-02-21: 0
|  | Create workflow | Van | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0
|  | Create database structure | Van | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0
| Code | Build UI for Login Screen | Luu | 8 | 8 | 2020-02-17: 0
|  | API document | Van | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0
|  | Config Firebase Back-end | Luu | 8 | 8 | 2020-02-17: 4; 2020-02-18: 0
|  | Config Firebase Mobile | Luu | 8 | 8 | 2020-02-17: 8; 2020-02-18: 4; 2020-02-19: 0
|  | Authentication Backend Facebook | Khai | 4 | 4 | 2020-02-17: 0; 2020-02-18: 8; 2020-02-19: 4; 2020-02-20: 0
|  | Authentication Mobile Facebook | Luu | 8 | 8 | 2020-02-17: 8; 2020-02-18: 8; 2020-02-19: 8; 2020-02-20: 4; 2020-02-21: 0
|  | Authentication Backend Google | Khai | 4 | 4 | 0 | 8 | 8 | 8 | 4 | 0
|  | Authentication Mobile Google | Luu | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 4 | 0
| Research | Research Android | Khai, Hieu | 80 | 80 | 72 | 56 | 40 | 24 | 8 | 0
|  | Search Firebase authentication | Van, Luu | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 4 | 0
| Testing | Test API Login | Hieu | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0
| Release Sprint 1 | Spring Review meeting | All member | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0
|  | Retrospective & Release | All member | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0
|  |  | Total | 304 | 304 | 240 | 200 | 144 | 104 | 72 | 48 | 28 | 20 | 16 | 0

## Actual
SPRINT 1 PLANNING
Team Availibility
| Name | Available Hours | Acutal Total
| Le Nguyen Hoang Van | 76 | 304 | [12 empty] | On Time
| Luong Minh Hieu | 76 | [13 empty] | Lately
| Tran Quang Khai | 76 | [13 empty] | Early
| Nguyen Dinh Luu | 76 | [13 empty] | Unfinished
Sprint | Component | Task name | Reponsible Member | Total | Actual | 2020-02-17 | 2020-02-18 | 2020-02-19 | 2020-02-20 | 2020-02-21 | 2020-02-24 | 2020-02-25 | 2020-02-26 | 2020-02-27 | 2020-02-28
1 | Initial Sprint 1 | Adjust backlog | All member | 96 | 96 | 2020-02-17: 64; 2020-02-18: 32; 2020-02-19: 0
|  | Config GCP | Van | 8 | 8 | 2020-02-17: 8; 2020-02-18: 0
|  | Create Gitlab repository | Van | 4 | 4 | 2020-02-17: 4; 2020-02-18: 4; 2020-02-19: 0
|  | Config Firebase | Van, Luu | 8 | 8 | 2020-02-17: 4; 2020-02-18: 4; 2020-02-19: 0
| Design | Create prototype | Van | 8 | 8 | 2020-02-17: 8; 2020-02-18: 8; 2020-02-19: 8; 2020-02-20: 0
|  | Create workflow | Van | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0
|  | Create database structure | Van | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0
| Code | Build UI for Login Screen | Luu | 8 | 8 | 2020-02-17: 0
|  | API document | Van | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0
|  | Config Firebase Back-end | Luu | 8 | 8 | 2020-02-17: 4; 2020-02-18: 0
|  | Config Firebase Mobile | Luu | 8 | 8 | 2020-02-17: 8; 2020-02-18: 4; 2020-02-19: 0
|  | Authentication Backend Facebook | Khai | 4 | 4 | 2020-02-17: 0; 2020-02-18: 8; 2020-02-19: 4; 2020-02-20: 0
|  | Authentication Mobile Facebook | Luu | 8 | 8 | 2020-02-17: 8; 2020-02-18: 8; 2020-02-19: 8; 2020-02-20: 4; 2020-02-21: 0
|  | Authentication Backend Google | Khai | 4 | 4 | 0 | 8 | 8 | 8 | 4 | 0
|  | Authentication Mobile Google | Luu | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 4 | 0
| Research | Research Android | Khai, Hieu | 80 | 80 | 2020-02-17: 72; 2020-02-18: 56; 2020-02-19: 40; 2020-02-20: 24; 2020-02-21: 0
|  | Search Firebase authentication | Van, Luu | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0
| Testing | Test API Login | Hieu | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0
| Release Sprint 1 | Spring Review meeting | All member | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0
|  | Retrospective & Release | All member | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0
|  |  | Total | 304 | 304 | 240 | 192 | 128 | 96 | 64 | 40 | 20 | 16 | 0 | 0

## Burn_down__Sprint1
Estimate | Actual | Date
240 | 240 | 2020-02-17
200 | 192 | 2020-02-18
144 | 128 | 2020-02-19
104 | 96 | 2020-02-20
72 | 64 | 2020-02-21
48 | 40 | 2020-02-24
28 | 20 | 2020-02-25
20 | 16 | 2020-02-26
16 | 0 | 2020-02-27
0 | 0 | 2020-02-28