## Estimated
SPRINT 2 PLANNING
Team Availibility
| Name | Available Hours | Estimation Total
| Le Nguyen Hoang Van | 76 | 304 | [12 empty] | On Time
| Luong Minh Hieu | 76 | [13 empty] | Lately
| Tran Quang Khai | 76 | [13 empty] | Early
| Nguyen Dinh Luu | 76 | [13 empty] | Unfinished
Sprint | Component | Task name | Reponsible Member | Total | Actual | 2020-03-02 | 2020-03-03 | 2020-03-04 | 2020-03-05 | 2020-03-06 | 2020-03-09 | 2020-03-10 | 2020-03-11 | 2020-03-12 | 2020-03-13
2 | Design | Recommend method | All member | 32 | 32 | 2020-03-02: 0
|  | Create TAGs | Van | 16 | 16 | 2020-03-02: 8; 2020-03-03: 0
|  | Create META-TAGs | Van | 16 | 16 | 2020-03-02: 16; 2020-03-03: 8; 2020-03-04: 0
|  | Create SUPER-TAGs | Van | 16 | 16 | 2020-03-02: 16; 2020-03-03: 16; 2020-03-04: 8; 2020-03-05: 0
| Code | Login implement | Luu | 8 | 8 | 2020-03-02: 0
|  | User information API | Van | 8 | 8 | 2020-03-02: 8; 2020-03-03: 8; 2020-03-04: 8; 2020-03-05: 8; 2020-03-06: 0
|  | Implement FCM Token | Luu | 16 | 16 | 2020-03-02: 16; 2020-03-03: 16; 2020-03-04: 16; 2020-03-05: 8; 2020-03-06: 0
|  | Data for recommend | Luu | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0
|  | Recommend API | Van | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0
|  | Location/show list items | Luu | 16 | 16 | 16 | 16 | 16 | 16 | 8 | 0
|  | Survey and Outside elements | Luu | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0
|  | Build UI for Survey screen | Khai | 32 | 32 | 2020-03-02: 24; 2020-03-03: 16; 2020-03-04: 8; 2020-03-05: 0
|  | Structure Android | Luu | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0
|  | Recommendation Algorithm | Khai | 32 | 32 | 32 | 32 | 32 | 24 | 16 | 8 | 0
| Testing | Test API Login | Hieu | 16 | 16 | 2020-03-02: 8; 2020-03-03: 0
|  | Test API Recommend | Hieu | 16 | 16 | 2020-03-02: 16; 2020-03-03: 8; 2020-03-04: 0
|  | Test Data | Hieu | 16 | 16 | 2020-03-02: 16; 2020-03-03: 16; 2020-03-04: 8; 2020-03-05: 0
|  | Test information API | Hieu | 16 | 16 | 2020-03-02: 16; 2020-03-03: 16; 2020-03-04: 16; 2020-03-05: 8; 2020-03-06: 0
| Release Sprint 2 | Spring Review meeting | All member | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0
|  | Retrospective & Release | All member | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0
|  |  | Total | 304 | 304 | 240 | 200 | 160 | 112 | 72 | 40 | 24 | 16 | 16 | 0

## Actual
SPRINT 2 PLANNING
Team Availibility
| Name | Available Hours | Acutal Total
| Le Nguyen Hoang Van | 76 | 304 | [12 empty] | On Time
| Luong Minh Hieu | 76 | [13 empty] | Lately
| Tran Quang Khai | 76 | [13 empty] | Early
| Nguyen Dinh Luu | 76 | [13 empty] | Unfinished
Sprint | Component | Task name | Reponsible Member | Total | Actual | 2020-03-02 | 2020-03-03 | 2020-03-04 | 2020-03-05 | 2020-03-06 | 2020-03-09 | 2020-03-10 | 2020-03-11 | 2020-03-12 | 2020-03-13
2 | Design | Recommend method | All member | 32 | 32 | 2020-03-02: 0
|  | Create TAGs | Van | 16 | 16 | 2020-03-02: 8; 2020-03-03: 8; 2020-03-04: 0
|  | Create META-TAGs | Van | 16 | 16 | 2020-03-02: 16; 2020-03-03: 8; 2020-03-04: 8; 2020-03-05: 0
|  | Create SUPER-TAGs | Van | 16 | 16 | 2020-03-02: 16; 2020-03-03: 16; 2020-03-04: 8; 2020-03-05: 8; 2020-03-06: 0
| Code | Login implement | Luu | 8 | 8 | 2020-03-02: 0
|  | User information API | Van | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0
|  | Implement FCM Token | Luu | 16 | 16 | 2020-03-02: 16; 2020-03-03: 16; 2020-03-04: 16; 2020-03-05: 8; 2020-03-06: 0
|  | Data for recommend | Luu | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0
|  | Recommend API | Van | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0
|  | Location/show list items | Luu | 16 | 16 | 16 | 16 | 16 | 16 | 8 | 0
|  | Survey and Outside elements | Luu | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0
|  | Build UI for Survey screen | Khai | 32 | 32 | 24 | 16 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8
|  | Structure Android | Luu | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0
|  | Recommendation Algorithm | Khai | 32 | 32 | 32 | 32 | 32 | 24 | 16 | 8 | 0
| Testing | Test API Login | Hieu | 16 | 16 | 2020-03-02: 0
|  | Test API Recommend | Hieu | 16 | 16 | 2020-03-02: 16; 2020-03-03: 0
|  | Test Data | Hieu | 16 | 16 | 2020-03-02: 16; 2020-03-03: 16; 2020-03-04: 0
|  | Test information API | Hieu | 16 | 16 | 2020-03-02: 16; 2020-03-03: 16; 2020-03-04: 16; 2020-03-05: 0
| Release Sprint 2 | Spring Review meeting | All member | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0
|  | Retrospective & Release | All member | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0
|  |  | Total | 304 | 304 | 232 | 200 | 160 | 120 | 88 | 56 | 32 | 24 | 24 | 8

## Burn_down__Sprint2
Estimate | Actual | Date
240 | 232 | 2020-03-02
200 | 200 | 2020-03-03
160 | 160 | 2020-03-04
112 | 120 | 2020-03-05
72 | 88 | 2020-03-06
40 | 56 | 2020-03-09
24 | 32 | 2020-03-10
16 | 24 | 2020-03-11
16 | 24 | 2020-03-12
0 | 8 | 2020-03-13