## Estimated
SPRINT 3 PLANNING
Team Availibility
| Name | Available Hours | Estimation Total
| Le Nguyen Hoang Van | 84 | 336 | [12 empty] | On Time
| Luong Minh Hieu | 84 | [13 empty] | Lately
| Tran Quang Khai | 84 | [13 empty] | Early
| Nguyen Dinh Luu | 84 | [13 empty] | Unfinished
Sprint | Component | Task name | Reponsible Member | Total | Actual | 2020-03-16 | 2020-03-17 | 2020-03-18 | 2020-03-19 | 2020-03-20 | 2020-03-23 | 2020-03-24 | 2020-03-25 | 2020-03-26 | 2020-03-27
3 | Initial Sprint 3 | Adjust backlog | All member | 32 | 32 | 2020-03-16: 0
|  | English presentation | All member | 32 | 32 | 2020-03-16: 32; 2020-03-17: 0
|  | Prototype documents | Van | 16 | 16 | 2020-03-16: 16; 2020-03-17: 16; 2020-03-18: 8; 2020-03-19: 0
| Code | Recommend - UI | Khai | 32 | 32 | 2020-03-16: 24; 2020-03-17: 16; 2020-03-18: 8; 2020-03-19: 0
|  | User information - UI | Hieu | 56 | 56 | 56 | 56 | 48 | 40 | 32 | 24 | 16 | 8 | 0
|  | Survey screen | Khai | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0
|  | Survey - Data | Van | 16 | 16 | 2020-03-16: 16; 2020-03-17: 16; 2020-03-18: 16; 2020-03-19: 8; 2020-03-20: 0
|  | API docs update | Van | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0
|  | Survey Image - API | Van | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0
|  | Survey - API | Van | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0
|  | Food detail - API | Van | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0
|  | Restaurant - API | Khai | 8 | 8 | 2020-03-16: 8; 2020-03-17: 8; 2020-03-18: 8; 2020-03-19: 8; 2020-03-20: 0
|  | Food detail - UI | Luu | 56 | 56 | 56 | 56 | 38 | 40 | 32 | 24 | 16 | 8 | 0
| Testing | Test Recommend UI | Khai | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0
|  | Test Survey screen | Luu | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0
|  | Test Survey - API | Hieu | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0
|  | Test food detail - UI | Khai | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0
|  | Test Restaurant - API | Khai | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0
| Release Sprint 3 | Spring Review meeting | All member | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0
|  | Retrospective & Release | All member | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0
|  |  | Total | 336 | 336 | 296 | 256 | 214 | 184 | 152 | 136 | 96 | 64 | 40 | 0

## Actual
SPRINT 3 PLANNING
Team Availibility
| Name | Available Hours | Acutal Total
| Le Nguyen Hoang Van | 84 | 336 | [12 empty] | On Time
| Luong Minh Hieu | 84 | [13 empty] | Lately
| Tran Quang Khai | 84 | [13 empty] | Early
| Nguyen Dinh Luu | 84 | [13 empty] | Unfinished
Sprint | Component | Task name | Reponsible Member | Total | Actual | 2020-03-16 | 2020-03-17 | 2020-03-18 | 2020-03-19 | 2020-03-20 | 2020-03-23 | 2020-03-24 | 2020-03-25 | 2020-03-26 | 2020-03-27
3 | Initial Sprint 3 | Adjust backlog | All member | 32 | 32 | 2020-03-16: 0
|  | English presentation | All member | 32 | 32 | 2020-03-16: 32; 2020-03-17: 0
|  | Prototype documents | Van | 16 | 16 | 2020-03-16: 8; 2020-03-17: 0
| Code | Recommend - UI | Khai | 32 | 32 | 24 | 16 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8
|  | User information - UI | Hieu | 56 | 56 | 56 | 56 | 48 | 40 | 32 | 24 | 16 | 8 | 8 | 8
|  | Survey screen | Khai | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8
|  | Survey - Data | Van | 16 | 16 | 2020-03-16: 16; 2020-03-17: 16; 2020-03-18: 16; 2020-03-19: 8; 2020-03-20: 0
|  | API docs update | Van | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0
|  | Survey Image - API | Van | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0
|  | Survey - API | Van | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0
|  | Food detail - API | Van | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0
|  | Restaurant - API | Khai | 8 | 8 | 2020-03-16: 8; 2020-03-17: 8; 2020-03-18: 8; 2020-03-19: 8; 2020-03-20: 0
|  | Food detail - UI | Luu | 56 | 56 | 56 | 56 | 38 | 40 | 32 | 24 | 16 | 8 | 8 | 8
| Testing | Test Recommend UI | Khai | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0
|  | Test Survey screen | Luu | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0
|  | Test Survey - API | Hieu | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0
|  | Test food detail - UI | Khai | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0
|  | Test Restaurant - API | Khai | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0
| Release Sprint 3 | Spring Review meeting | All member | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0
|  | Retrospective & Release | All member | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0
|  |  | Total | 336 | 336 | 288 | 240 | 206 | 192 | 160 | 136 | 88 | 64 | 56 | 32

## Burn_down__Sprint3
Estimate | Actual | Date
296 | 288 | 2020-03-16
256 | 240 | 2020-03-17
214 | 206 | 2020-03-18
184 | 192 | 2020-03-19
152 | 160 | 2020-03-20
136 | 136 | 2020-03-23
96 | 88 | 2020-03-24
64 | 64 | 2020-03-25
40 | 56 | 2020-03-26
0 | 32 | 2020-03-27