## Estimated
SPRINT 4 PLANNING
Team Availibility
| Name | Available Hours | Estimation Total
| Le Nguyen Hoang Van | 76 | 304 | [12 empty] | On Time
| Luong Minh Hieu | 76 | [13 empty] | Lately
| Tran Quang Khai | 76 | [13 empty] | Early
| Nguyen Dinh Luu | 76 | [13 empty] | Unfinished
Sprint | Component | Task name | Reponsible Member | Total | Actual | 2020-03-30 | 2020-03-31 | 2020-04-01 | 2020-04-02 | 2020-04-03 | 2020-04-06 | 2020-04-07 | 2020-04-08 | 2020-04-09 | 2020-04-10
4 | Code | Search dishes - API | Van | 8 | 8 | 0
|  | Update project plan | Van | 8 | 8 | 8 | 0
|  | Meals today - API | Van | 8 | 8 | 8 | 8 | 0
|  | Fix rating API in case skip survey | Van | 8 | 8 | 8 | 8 | 8 | 0
|  | Meals today - Data | Van | 8 | 8 | 8 | 8 | 8 | 8 | 0
|  | More-Bookmark - API | Van | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0
|  | Allergy data | Van | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0
|  | Recommendation - Feature | Khai | 16 | 16 | 8 | 0
|  | Finish recommend screen | Khai | 8 | 8 | 8 | 8 | 0
|  | More-Bookmark - UI | Khai | 8 | 8 | 8 | 8 | 8 | 0
|  | More-Bookmark - Function | Khai | 16 | 16 | 16 | 16 | 16 | 16 | 8 | 0
|  | Optimize source back-end | Van | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0
|  | Update slides for presentation | Luu | 16 | 16 | 8 | 0
|  | Handle META-TAGs | Van | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0
|  | Survey - feature | Khai | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0
|  | Search dishes - UI | Khai | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0
|  | Search dishes - Function | Khai | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0
|  | User information feature | Hieu | 16 | 16 | 8 | 0
|  | Finish user info screen | Hieu | 16 | 16 | 16 | 16 | 8 | 0
|  | More - UI | Hieu | 16 | 16 | 16 | 16 | 16 | 16 | 8 | 0
|  | More-profile UI | Hieu | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0
|  | Detail food - Feature | Luu | 40 | 40 | 40 | 40 | 32 | 24 | 16 | 8 | 0
|  | Splash screen | Hieu | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 8 | 0
|  | Meals today screen - UI | Luu | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 8 | 0
| Release Sprint 4 | Spring Review meeting | All member | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0
|  | Retrospective & Release | All member | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0
|  |  | Total | 304 | 304 | 272 | 240 | 208 | 176 | 144 | 112 | 80 | 48 | 16 | 0

## Actual
SPRINT 1 PLANNING
Team Availibility
| Name | Available Hours | Acutal Total
| Le Nguyen Hoang Van | 76 | 304 | [12 empty] | On Time
| Luong Minh Hieu | 76 | [13 empty] | Lately
| Tran Quang Khai | 76 | [13 empty] | Early
| Nguyen Dinh Luu | 76 | [13 empty] | Unfinished
Sprint | Component | Task name | Reponsible Member | Total | Actual | 2020-03-30 | 2020-03-31 | 2020-04-01 | 2020-04-02 | 2020-04-03 | 2020-04-06 | 2020-04-07 | 2020-04-08 | 2020-04-09 | 2020-04-10
4 | Code | Search dishes - API | Van | 8 | 8 | 0
|  | Update project plan | Van | 8 | 8 | 8 | 0
|  | Meals today - API | Van | 8 | 8 | 8 | 0
|  | Fix rating API in case skip survey | Van | 8 | 8 | 8 | 8 | 0
|  | Meals today - Data | Van | 8 | 8 | 8 | 8 | 8 | 0
|  | More-Bookmark - API | Van | 8 | 8 | 8 | 8 | 8 | 8 | 0
|  | Allergy data | Van | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0
|  | Recommendation - Feature | Khai | 16 | 16 | 8 | 0
|  | Finish recommend screen | Khai | 8 | 8 | 8 | 8 | 0
|  | More-Bookmark - UI | Khai | 8 | 8 | 8 | 8 | 8 | 0
|  | More-Bookmark - Function | Khai | 16 | 16 | 16 | 16 | 16 | 16 | 8 | 0
|  | Optimize source back-end | Van | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0
|  | Update slides for presentation | Luu | 16 | 16 | 8 | 0
|  | Handle META-TAGs | Van | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0
|  | Survey - feature | Khai | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8
|  | Search dishes - UI | Khai | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0
|  | Search dishes - Function | Khai | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0
|  | User information feature | Hieu | 16 | 16 | 8 | 8 | 8 | 8 | 0
|  | Finish user info screen | Hieu | 16 | 16 | 16 | 16 | 8 | 8 | 8 | 0
|  | More - UI | Hieu | 16 | 16 | 16 | 16 | 16 | 16 | 8 | 8 | 8 | 8 | 0
|  | More-profile UI | Hieu | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8
|  | Detail food - Feature | Luu | 40 | 40 | 40 | 40 | 32 | 24 | 16 | 8 | 8 | 8 | 8 | 8
|  | Splash screen | Hieu | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 8 | 0
|  | Meals today screen - UI | Luu | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 8 | 8 | 8
| Release Sprint 4 | Spring Review meeting | All member | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0
|  | Retrospective & Release | All member | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0
|  |  | Total | 304 | 304 | 272 | 240 | 208 | 184 | 144 | 112 | 104 | 72 | 48 | 32

## Burn_down__Sprint4
Estimate | Actual | Date
272 | 272 | 2020-03-30
240 | 240 | 2020-03-31
208 | 208 | 2020-04-01
176 | 184 | 2020-04-02
144 | 144 | 2020-04-03
112 | 112 | 2020-04-06
80 | 104 | 2020-04-07
48 | 72 | 2020-04-08
16 | 48 | 2020-04-09
0 | 32 | 2020-04-10