## Estimated
SPRINT 1 PLANNING
Team Availibility
| Name | Available Hours | Estimation Total
| Le Nguyen Hoang Van | 84 | 336 | [12 empty] | On Time
| Luong Minh Hieu | 84 | [13 empty] | Lately
| Tran Quang Khai | 84 | [13 empty] | Early
| Nguyen Dinh Luu | 84 | [13 empty] | Unfinished
Sprint | Component | Task name | Reponsible Member | Total | Actual | 2020-04-13 | 2020-04-14 | 2020-04-15 | 2020-04-16 | 2020-04-17 | 2020-04-20 | 2020-04-21 | 2020-04-22 | 2020-04-23 | 2020-04-24
1 | Code | Bookmark screen | Khai | 32 | 32 | 2020-04-13: 24; 2020-04-14: 16; 2020-04-15: 8; 2020-04-16: 0
|  | Multiple languages | Khai | 16 | 16 | 16 | 16 | 16 | 16 | 8 | 0
|  | Apply algorithmn for rating | Van | 8 | 8 | 2020-04-13: 0
|  | Call API History in recommend screen | Khai | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0
|  | Update proposal | Van | 8 | 8 | 2020-04-13: 8; 2020-04-14: 0
|  | Get list Allergy | Van | 8 | 8 | 2020-04-13: 8; 2020-04-14: 8; 2020-04-15: 0
|  | Add latittude, longitude to recommend food | Van | 8 | 8 | 2020-04-13: 8; 2020-04-14: 8; 2020-04-15: 8; 2020-04-16: 0
|  | Meals today screen | Luu | 24 | 24 | 2020-04-13: 16; 2020-04-14: 8; 2020-04-15: 0
|  | Delete allergy | Hieu | 8 | 8 | 2020-04-13: 0
|  | Handle push notification in client | Luu | 8 | 8 | 2020-04-13: 8; 2020-04-14: 8; 2020-04-15: 8; 2020-04-16: 0
|  | History Screen - UI | Khai | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0
|  | Survey Screen - UI | Khai | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0
|  | Unittest backend | Van | 8 | 8 | 2020-04-13: 8; 2020-04-14: 8; 2020-04-15: 8; 2020-04-16: 8; 2020-04-17: 0
|  | Detail food screen | Luu | 8 | 8 | 2020-04-13: 8; 2020-04-14: 8; 2020-04-15: 8; 2020-04-16: 8; 2020-04-17: 0
|  | Search Screen - UI | Khai | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0
|  | Fix image URL response | Van | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0
|  | Spark environment | Van | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0
|  | Allergy handle for recommend screen | Hieu | 8 | 8 | 2020-04-13: 8; 2020-04-14: 0
|  | History Screen -API | Hieu | 8 | 8 | 2020-04-13: 8; 2020-04-14: 8; 2020-04-15: 0
|  | Add description for API survey and Search | Van | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0
|  | Improve UI with Adobe XD | Van | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0
|  | Push notification | Luu | 8 | 8 | 2020-04-13: 8; 2020-04-14: 8; 2020-04-15: 8; 2020-04-16: 8; 2020-04-17: 0
|  | Update detail food API | Van | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0
|  | More-UI | Hieu | 8 | 8 | 2020-04-13: 8; 2020-04-14: 8; 2020-04-15: 8; 2020-04-16: 0
|  | Meals today screen - function | Luu | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0
|  | Get location | Hieu | 8 | 8 | 2020-04-13: 8; 2020-04-14: 8; 2020-04-15: 8; 2020-04-16: 8; 2020-04-17: 0
|  | Build APK | Luu | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0
|  | Information screen | Hieu | 8 | 8 | 2020-04-13: 8; 2020-04-14: 8; 2020-04-15: 8; 2020-04-16: 8; 2020-04-17: 0
|  | Information screen - Function | Hieu | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0
|  | Profile | Hieu | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0
|  | Profile - Function | Hieu | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0
| Testing | Test and fix UI | Hieu | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0
|  | Test API | Luu | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0
|  | Fix bugs in application | Luu | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0
| Release Sprint 1 | Spring Review meeting | All member | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0
|  | Retrospective & Release | All member | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0
|  |  | Total | 336 | 336 | 304 | 272 | 240 | 208 | 160 | 128 | 96 | 64 | 32 | 0

## Actual
SPRINT 1 PLANNING
Team Availibility
| Name | Available Hours | Acutal Total
| Le Nguyen Hoang Van | 84 | 336 | [12 empty] | On Time
| Luong Minh Hieu | 84 | [13 empty] | Lately
| Tran Quang Khai | 84 | [13 empty] | Early
| Nguyen Dinh Luu | 84 | [13 empty] | Unfinished
Sprint | Component | Task name | Reponsible Member | Total | Actual | 2020-04-13 | 2020-04-14 | 2020-04-15 | 2020-04-16 | 2020-04-17 | 2020-04-20 | 2020-04-21 | 2020-04-22 | 2020-04-23 | 2020-04-24
1 | Code | Bookmark screen | Khai | 32 | 32 | 2020-04-13: 24; 2020-04-14: 8; 2020-04-15: 0; 2020-04-16: 0
|  | Multiple languages | Khai | 16 | 16 | 16 | 16 | 16 | 8 | 0 | 0
|  | Apply algorithmn for rating | Van | 8 | 8 | 2020-04-13: 0
|  | Call API History in recommend screen | Khai | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 0
|  | Update proposal | Van | 8 | 8 | 2020-04-13: 8; 2020-04-14: 0
|  | Get list Allergy | Van | 8 | 8 | 2020-04-13: 8; 2020-04-14: 8; 2020-04-15: 0
|  | Add latittude, longitude to recommend food | Van | 8 | 8 | 2020-04-13: 8; 2020-04-14: 8; 2020-04-15: 8; 2020-04-16: 0
|  | Meals today screen | Luu | 24 | 24 | 2020-04-13: 16; 2020-04-14: 8; 2020-04-15: 0
|  | Delete allergy | Hieu | 8 | 8 | 2020-04-13: 0
|  | Handle push notification in client | Luu | 8 | 8 | 2020-04-13: 8; 2020-04-14: 8; 2020-04-15: 8; 2020-04-16: 0
|  | History Screen - UI | Khai | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0
|  | Survey Screen - UI | Khai | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0
|  | Unittest backend | Van | 8 | 8 | 2020-04-13: 8; 2020-04-14: 8; 2020-04-15: 8; 2020-04-16: 8; 2020-04-17: 0
|  | Detail food screen | Luu | 8 | 8 | 2020-04-13: 8; 2020-04-14: 8; 2020-04-15: 8; 2020-04-16: 8; 2020-04-17: 0
|  | Search Screen - UI | Khai | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0
|  | Fix image URL response | Van | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0
|  | Spark environment | Van | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0
|  | Allergy handle for recommend screen | Hieu | 8 | 8 | 2020-04-13: 8; 2020-04-14: 0
|  | History Screen -API | Hieu | 8 | 8 | 2020-04-13: 8; 2020-04-14: 8; 2020-04-15: 0
|  | Add description for API survey and Search | Van | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0
|  | Improve UI with Adobe XD | Van | 8 | 8 | 2020-04-13: 0
|  | Push notification | Luu | 8 | 8 | 2020-04-13: 8; 2020-04-14: 8; 2020-04-15: 8; 2020-04-16: 8; 2020-04-17: 0
|  | Update detail food API | Van | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0
|  | More-UI | Hieu | 8 | 8 | 2020-04-13: 8; 2020-04-14: 8; 2020-04-15: 8; 2020-04-16: 0
|  | Meals today screen - function | Luu | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0
|  | Get location | Hieu | 8 | 8 | 2020-04-13: 8; 2020-04-14: 8; 2020-04-15: 8; 2020-04-16: 8; 2020-04-17: 0
|  | Build APK | Luu | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 0
|  | Information screen | Hieu | 8 | 8 | 2020-04-13: 8; 2020-04-14: 8; 2020-04-15: 8; 2020-04-16: 0
|  | Information screen - Function | Hieu | 8 | 8 | 2020-04-13: 8; 2020-04-14: 8; 2020-04-15: 8; 2020-04-16: 8; 2020-04-17: 0
|  | Profile | Hieu | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0
|  | Profile - Function | Hieu | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0
| Testing | Test and fix UI | Hieu | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0
|  | Test API | Luu | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0
|  | Fix bugs in application | Luu | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0
| Release Sprint 1 | Spring Review meeting | All member | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 0
|  | Retrospective & Release | All member | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 0
|  |  | Total | 336 | 336 | 296 | 256 | 224 | 184 | 136 | 88 | 56 | 24 | 0 | 0

## Burn_down__Sprint1
Estimate | Actual | Date
304 | 296 | 2020-04-13
272 | 256 | 2020-04-14
240 | 224 | 2020-04-15
208 | 184 | 2020-04-16
160 | 136 | 2020-04-17
128 | 88 | 2020-04-20
96 | 56 | 2020-04-21
64 | 24 | 2020-04-22
32 | 0 | 2020-04-23
0 | 0 | 2020-04-24